## Holidays
Christmas Day | 2017-12-25 | 2018
New Years Day | 2018-01-01
Lee-Jackson Day | 2018-01-12
Martin Luther King, Jr. Day | 2018-01-15
Presidents Day | 2018-02-19
Memorial Day | 2018-05-28
Independence Day | 2018-07-04
Labor Day | 2018-09-03
Columbus Day | 2018-10-08
Veterans Day | 2018-11-12
Thanksgiving Day | 2018-11-22
Day After Thanksgiving | 2018-11-23
Christmas Day | 2018-12-25 | 2019
New Years Day | 2019-01-01
Lee-Jackson Day | 2019-01-18
Martin Luther King, Jr. Day | 2019-01-21
Presidents Day | 2019-02-18
Memorial Day | 2019-05-27
Independence Day | 2019-07-04
Labor Day | 2019-09-02
Columbus Day | 2019-10-14
Veterans Day | 2019-11-11
Thanksgiving Day | 2019-11-28
Day After Thanksgiving | 2019-11-29
Christmas Day | 2019-12-25 | 2020
New Years Day | 2020-01-01
Lee-Jackson Day | 2020-01-17
Martin Luther King, Jr. Day | 2020-01-20
Presidents Day | 2020-02-17
Memorial Day | 2020-05-25
Independence Day | 2020-07-03
Labor Day | 2020-09-07
Columbus Day | 2020-10-12
Veterans Day | 2020-11-11
Thanksgiving Day | 2020-11-26
Day After Thanksgiving | 2020-11-27
Christmas Day | 2020-12-25 | 2021
New Years Day | 2021-01-01
Lee-Jackson Day | 2021-01-15
Martin Luther King, Jr. Day | 2021-01-18
Presidents Day | 2021-02-15
Memorial Day | 2021-05-31
Independence Day | 2021-07-05
Labor Day | 2021-09-06
Columbus Day | 2021-10-11
Veterans Day | 2021-11-11
Thanksgiving Day | 2021-11-25
Day After Thanksgiving | 2021-11-26
Christmas Day | 2021-12-24 | 2022
New Years Day | 2022-01-01
Lee-Jackson Day | 2022-01-14
Martin Luther King, Jr. Day | 2022-01-17
Presidents Day | 2022-02-21
Memorial Day | 2022-05-30
Independence Day | 2022-07-04
Labor Day | 2022-09-05
Columbus Day | 2022-10-10
Veterans Day | 2022-11-11
Thanksgiving Day | 2022-11-24
Day After Thanksgiving | 2022-11-25
Christmas Day | 2022-12-24 | 2023
New Years Day | 2023-01-02
Lee-Jackson Day | 2023-01-13
Martin Luther King, Jr. Day | 2023-01-16
Presidents Day | 2023-02-20
Memorial Day | 2023-05-29
Independence Day | 2023-07-04
Labor Day | 2023-09-04
Columbus Day | 2023-10-09
Veterans Day | 2023-11-10
Thanksgiving Day | 2023-11-23
Day After Thanksgiving | 2023-11-24
Christmas Day | 2023-12-25 | 2024
New Years Day | 2024-01-01
Lee-Jackson Day | 2024-01-12
Martin Luther King, Jr. Day | 2024-01-15
Presidents Day | 2024-02-19
Memorial Day | 2024-05-27
Independence Day | 2024-07-04
Labor Day | 2024-09-02
Columbus Day | 2024-10-14
Veterans Day | 2024-11-11
Thanksgiving Day | 2024-11-28
Day After Thanksgiving | 2024-11-29
Christmas Day | 2024-12-25 | 2025
New Years Day | 2025-01-01
Lee-Jackson Day | 2025-01-17
Martin Luther King, Jr. Day | 2025-01-20
Presidents Day | 2025-02-17
Memorial Day | 2025-05-26
Independence Day | 2025-07-04
Labor Day | 2025-09-01
Columbus Day | 2025-10-13
Veterans Day | 2025-11-11
Thanksgiving Day | 2025-11-27
Day After Thanksgiving | 2025-11-28
Christmas Day | 2025-12-25
New Years Day | 2026-01-01 | 2026
Lee-Jackson Day | 2026-01-16
Martin Luther King, Jr. Day | 2026-01-19
Presidents Day | 2026-02-16
Memorial Day | 2026-05-25
Independence Day | 2026-07-03
Labor Day | 2026-09-07
Columbus Day | 2026-10-12
Veterans Day | 2026-11-11
Thanksgiving Day | 2026-11-26
Day After Thanksgiving | 2026-11-27
Christmas Day | 2026-12-25
New Years Day | 2027-01-01 | 2027
Lee-Jackson Day | 2027-01-15
Martin Luther King, Jr. Day | 2027-01-18
Presidents Day | 2027-02-15
Memorial Day | 2027-05-31
Independence Day | 2027-07-05
Labor Day | 2027-09-06
Columbus Day | 2027-10-11
Veterans Day | 2027-11-11
Thanksgiving Day | 2027-11-25
Day After Thanksgiving | 2027-11-26
Christmas Day | 2027-12-24
New Years Day | 2027-12-31 | 2028
Lee-Jackson Day | 2028-01-14
Martin Luther King, Jr. Day | 2028-01-17
Presidents Day | 2028-02-21
Memorial Day | 2028-05-29
Independence Day | 2028-07-04
Labor Day | 2028-09-04
Columbus Day | 2028-10-09
Veterans Day | 2028-11-10
Thanksgiving Day | 2028-11-23
Day After Thanksgiving | 2028-11-24
Christmas Day | 2028-12-25
New Years Day | 2028-12-31 | 2029
Lee-Jackson Day | 2029-01-12
Martin Luther King, Jr. Day | 2029-01-15
Presidents Day | 2029-02-19
Memorial Day | 2029-05-28
Independence Day | 2029-07-04
Labor Day | 2029-09-03
Columbus Day | 2029-10-08
Veterans Day | 2029-11-12
Thanksgiving Day | 2029-11-22
Day After Thanksgiving | 2029-11-23
Christmas Day | 2029-12-25
New Years Day | 2029-12-31 | 2030
Lee-Jackson Day | 2030-01-18
Martin Luther King, Jr. Day | 2030-01-21
Presidents Day | 2030-02-18
Memorial Day | 2030-05-27
Independence Day | 2030-07-04
Labor Day | 2030-09-02
Columbus Day | 2030-10-14
Veterans Day | 2030-11-11
Thanksgiving Day | 2030-11-28
Day After Thanksgiving | 2030-11-29
Christmas Day | 2030-12-25
| 2030-12-31 | 2031
2031-01-17
2031-01-20
2031-02-17
2031-05-26
2031-07-04
2031-09-01
2031-10-13
2031-11-11
2031-11-27
2031-11-28
2031-12-25

## Read Me If Viewing Errors
If you are getting errors in the date fields in RAAP 2007 Worksheet and above:
Go to Tools
Add Ins
Put a check in "Analysis Tool Pack"
Put a check in "Conditional Sum Wizard"
Put a check in "Solver Add In"
You May Have to Restart your PC
The Values Should Now Appear In the Date Field.

## Sheet1
These are the instructions for revising the dates for the Bid letting and advertisement on the First (RAAP),
advertisement and the second (SAAP) ad dates.
RAAP Advertisement Dates
Second Tuesday of every month.
SAAP Advertisement Dates
Fourth Tuesday every month except December
when it is the third Tuesday.

## SAAP 2015-2026
SEE CUT-OFF DATES FOR TIER 1 ADVERTISEMENT

## RAAP 2018
Rev 8/29/18
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2018
File Location: Current Drawings | File Location: Plan File Room | File Location: Plan File Room | [5 empty] | File Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2017-08-08 | 2017-08-22 | 2017-09-01 | 2017-09-08 | 2017-09-12 | 2017-10-18 | 2017-11-01 | 2017-11-13 | 2017-11-16 | 2017-11-29 |  | 2017-12-06 | 2018-01-09
2017-09-08 | 2017-09-22 | 2017-10-04 | 2017-10-11 | 2017-10-13 | 2017-11-20 | 2017-12-04 | 2017-12-14 | 2017-12-19 | 2018-01-03 |  | 2018-01-10 | 2018-02-13
2017-10-05 | 2017-10-19 | 2017-10-31 | 2017-11-07 | 2017-11-09 | 2017-12-15 | 2018-01-02 | 2018-01-16 | 2018-01-19 | 2018-02-01 |  | 2018-02-08 | 2018-03-13
2017-11-02 | 2017-11-16 | 2017-11-28 | 2017-12-05 | 2017-12-07 | 2018-01-18 | 2018-02-01 | 2018-02-13 | 2018-02-16 | 2018-03-02 |  | 2018-03-09 | 2018-04-10
2017-11-30 | 2017-12-14 | 2017-12-27 | 2018-01-04 | 2018-01-08 | 2018-02-15 | 2018-03-02 | 2018-03-14 | 2018-03-19 | 2018-03-30 |  | 2018-04-06 | 2018-05-08
2018-01-05 | 2018-01-23 | 2018-02-02 | 2018-02-09 | 2018-02-13 | 2018-03-22 | 2018-04-05 | 2018-04-17 | 2018-04-20 | 2018-05-03 |  | 2018-05-10 | 2018-06-12
2018-02-05 | 2018-02-20 | 2018-03-02 | 2018-03-09 | 2018-03-13 | 2018-04-18 | 2018-05-02 | 2018-05-14 | 2018-05-17 | 2018-05-31 |  | 2018-06-07 | 2018-07-10
2018-03-13 | 2018-03-27 | 2018-04-06 | 2018-04-13 | 2018-04-17 | 2018-05-23 | 2018-06-07 | 2018-06-19 | 2018-06-22 | 2018-07-06 |  | 2018-07-13 | 2018-08-14
2018-04-09 | 2018-04-23 | 2018-05-03 | 2018-05-10 | 2018-05-14 | 2018-06-20 | 2018-07-05 | 2018-07-17 | 2018-07-20 | 2018-08-02 |  | 2018-08-09 | 2018-09-11
2018-05-04 | 2018-05-18 | 2018-05-31 | 2018-06-07 | 2018-06-11 | 2018-07-18 | 2018-08-01 | 2018-08-13 | 2018-08-16 | 2018-08-29 |  | 2018-09-06 | 2018-10-09
2018-06-04 | 2018-06-18 | 2018-06-28 | 2018-07-06 | 2018-07-10 | 2018-08-15 | 2018-08-29 | 2018-09-11 | 2018-09-14 | 2018-09-27 |  | 2018-10-04 | 2018-11-06
2018-06-27 | 2018-07-12 | 2018-07-24 | 2018-07-31 | 2018-08-02 | 2018-09-10 | 2018-09-24 | 2018-10-04 | 2018-10-10 | 2018-10-23 |  | 2018-10-30 | 2018-12-04
2018-06-27: 68 END; 2018-07-31: 71, 79 BEG; 2018-08-02: 72 BEG; 2018-10-10: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2018-10-23: 63 END |  | 80 BEG | 80 END
2018-06-27: 70 END; 2018-07-31: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2018-10-23: 71 END |  | 72 END
2018-06-27: 71X; 2018-10-23: 72X | 6
2018-06-27: 71C END; 2018-10-23: 21A,B END | 9
2018-10-10: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2018-10-23: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2019
REV. 8/29/18
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2019
File Location: Current Drawings | File Location: Plan File Room | File Location: Plan File Room | [5 empty] | File Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2018-07-31 | 2018-08-14 | 2018-08-24 | 2018-08-31 | 2018-09-05 | 2018-10-12 | 2018-10-26 | 2018-11-07 | 2018-11-13 | 2018-11-28 |  | 2018-12-05 | 2019-01-08
2018-08-31 | 2018-09-17 | 2018-09-27 | 2018-10-04 | 2018-10-09 | 2018-11-15 | 2018-12-03 | 2018-12-13 | 2018-12-18 | 2019-01-02 |  | 2019-01-09 | 2019-02-12
2018-09-28 | 2018-10-15 | 2018-10-25 | 2018-11-01 | 2018-11-05 | 2018-12-14 | 2018-12-31 | 2019-01-11 | 2019-01-16 | 2019-01-31 |  | 2019-02-07 | 2019-03-12
2018-10-29 | 2018-11-13 | 2018-11-27 | 2018-12-04 | 2018-12-06 | 2019-01-15 | 2019-01-31 | 2019-02-12 | 2019-02-15 | 2019-03-01 |  | 2019-03-08 | 2019-04-09
2018-11-29 | 2018-12-13 | 2018-12-26 | 2019-01-03 | 2019-01-07 | 2019-02-14 | 2019-03-01 | 2019-03-13 | 2019-03-18 | 2019-03-29 |  | 2019-04-05 | 2019-05-07
2019-01-04 | 2019-01-22 | 2019-02-01 | 2019-02-08 | 2019-02-12 | 2019-03-21 | 2019-04-04 | 2019-04-16 | 2019-04-19 | 2019-05-02 |  | 2019-05-09 | 2019-06-11
2019-02-04 | 2019-02-19 | 2019-03-01 | 2019-03-08 | 2019-03-12 | 2019-04-17 | 2019-05-01 | 2019-05-13 | 2019-05-16 | 2019-05-30 |  | 2019-06-06 | 2019-07-09
2019-03-12 | 2019-03-26 | 2019-04-05 | 2019-04-12 | 2019-04-16 | 2019-05-22 | 2019-06-06 | 2019-06-18 | 2019-06-21 | 2019-07-05 |  | 2019-07-12 | 2019-08-13
2019-04-08 | 2019-04-22 | 2019-05-02 | 2019-05-09 | 2019-05-13 | 2019-06-19 | 2019-07-03 | 2019-07-16 | 2019-07-19 | 2019-08-01 |  | 2019-08-08 | 2019-09-10
2019-05-06 | 2019-05-20 | 2019-05-31 | 2019-06-07 | 2019-06-11 | 2019-07-18 | 2019-08-01 | 2019-08-13 | 2019-08-16 | 2019-08-29 |  | 2019-09-06 | 2019-10-08
2019-06-03 | 2019-06-17 | 2019-06-27 | 2019-07-05 | 2019-07-09 | 2019-08-14 | 2019-08-28 | 2019-09-10 | 2019-09-13 | 2019-09-26 |  | 2019-10-03 | 2019-11-05
2019-07-03 | 2019-07-18 | 2019-07-30 | 2019-08-06 | 2019-08-08 | 2019-09-16 | 2019-09-30 | 2019-10-10 | 2019-10-16 | 2019-10-29 |  | 2019-11-05 | 2019-12-10
[5 empty] | -12 |  |  |  | -5
2019-07-03: 68 END; 2019-08-06: 71, 79 BEG; 2019-08-08: 72 BEG; 2019-10-16: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2019-10-29: 63 END |  | 80 BEG | 80 END
2019-07-03: 70 END; 2019-08-06: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2019-10-29: 71 END |  | 72 END
2019-07-03: 71X; 2019-10-29: 72X | 6
2019-07-03: 71C END; 2019-10-29: 21A,B END | 9
2019-10-16: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2019-10-29: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2020
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2020
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2019-07-30 | 2019-08-13 | 2019-08-23 | 2019-08-30 | 2019-09-04 | 2019-10-10 | 2019-10-25 | 2019-11-06 | 2019-11-12 | 2019-11-25 |  | 2019-12-04 | 2020-01-07
2019-08-30 | 2019-09-16 | 2019-09-26 | 2019-10-03 | 2019-10-07 | 2019-11-14 | 2019-12-02 | 2019-12-12 | 2019-12-17 | 2019-12-31 |  | 2020-01-08 | 2020-02-11
2019-09-27 | 2019-10-11 | 2019-10-24 | 2019-10-31 | 2019-11-04 | 2019-12-13 | 2019-12-30 | 2020-01-10 | 2020-01-15 | 2020-01-30 |  | 2020-02-06 | 2020-03-10
2019-10-28 | 2019-11-12 | 2019-11-22 | 2019-12-03 | 2019-12-05 | 2020-01-14 | 2020-01-30 | 2020-02-11 | 2020-02-14 | 2020-02-28 |  | 2020-03-06 | 2020-04-07
2019-11-26 | 2019-12-12 | 2019-12-24 | 2020-01-02 | 2020-01-06 | 2020-02-13 | 2020-02-28 | 2020-03-11 | 2020-03-16 | 2020-03-27 |  | 2020-04-03 | 2020-05-05
2020-01-03 | 2020-01-21 | 2020-01-31 | 2020-02-07 | 2020-02-11 | 2020-03-19 | 2020-04-02 | 2020-04-14 | 2020-04-17 | 2020-04-30 |  | 2020-05-07 | 2020-06-09
2020-02-03 | 2020-02-18 | 2020-02-28 | 2020-03-06 | 2020-03-10 | 2020-04-15 | 2020-04-29 | 2020-05-11 | 2020-05-14 | 2020-05-28 |  | 2020-06-04 | 2020-07-07
2020-03-10 | 2020-03-24 | 2020-04-03 | 2020-04-10 | 2020-04-14 | 2020-05-20 | 2020-06-04 | 2020-06-16 | 2020-06-19 | 2020-07-02 |  | 2020-07-10 | 2020-08-11
2020-04-06 | 2020-04-20 | 2020-04-30 | 2020-05-07 | 2020-05-11 | 2020-06-17 | 2020-07-01 | 2020-07-14 | 2020-07-17 | 2020-07-30 |  | 2020-08-06 | 2020-09-08
2020-05-04 | 2020-05-18 | 2020-05-29 | 2020-06-05 | 2020-06-09 | 2020-07-16 | 2020-07-30 | 2020-08-11 | 2020-08-14 | 2020-08-27 |  | 2020-09-03 | 2020-10-06
2020-06-02 | 2020-06-16 | 2020-06-26 | 2020-07-06 | 2020-07-08 | 2020-08-13 | 2020-08-27 | 2020-09-09 | 2020-09-14 | 2020-09-25 |  | 2020-10-02 | 2020-11-04
2020-07-01 | 2020-07-16 | 2020-07-28 | 2020-08-04 | 2020-08-06 | 2020-09-14 | 2020-09-28 | 2020-10-08 | 2020-10-14 | 2020-10-27 |  | 2020-11-03 | 2020-12-08
-3
2020-07-01: 68 END; 2020-08-04: 71, 79 BEG; 2020-08-06: 72 BEG; 2020-10-14: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2020-10-27: 63 END |  | 80 BEG | 80 END
2020-07-01: 70 END; 2020-08-04: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2020-10-27: 71 END |  | 72 END
2020-07-01: 71X; 2020-10-27: 72X | 6
2020-07-01: 71C END; 2020-10-27: 21A,B END | 9
2020-10-14: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2020-10-27: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2021
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2021
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2020-08-04 | 2020-08-18 | 2020-08-28 | 2020-09-04 | 2020-09-09 | 2020-10-16 | 2020-10-30 | 2020-11-12 | 2020-11-17 | 2020-12-02 |  | 2020-12-09 | 2021-01-12
2020-08-28 | 2020-09-14 | 2020-09-24 | 2020-10-01 | 2020-10-05 | 2020-11-12 | 2020-11-30 | 2020-12-10 | 2020-12-15 | 2020-12-29 |  | 2021-01-06 | 2021-02-09
2020-09-25 | 2020-10-09 | 2020-10-22 | 2020-10-29 | 2020-11-02 | 2020-12-11 | 2020-12-28 | 2021-01-08 | 2021-01-13 | 2021-01-28 |  | 2021-02-04 | 2021-03-09
2020-11-02 | 2020-11-17 | 2020-12-01 | 2020-12-08 | 2020-12-10 | 2021-01-21 | 2021-02-04 | 2021-02-17 | 2021-02-22 | 2021-03-05 |  | 2021-03-12 | 2021-04-13
2020-12-03 | 2020-12-17 | 2020-12-30 | 2021-01-07 | 2021-01-11 | 2021-02-19 | 2021-03-05 | 2021-03-17 | 2021-03-22 | 2021-04-02 |  | 2021-04-09 | 2021-05-11
2020-12-31 | 2021-01-19 | 2021-01-29 | 2021-02-05 | 2021-02-09 | 2021-03-18 | 2021-04-01 | 2021-04-13 | 2021-04-16 | 2021-04-29 |  | 2021-05-06 | 2021-06-08
2021-02-08 | 2021-02-23 | 2021-03-05 | 2021-03-12 | 2021-03-16 | 2021-04-21 | 2021-05-05 | 2021-05-17 | 2021-05-20 | 2021-06-03 |  | 2021-06-10 | 2021-07-13
2021-03-09 | 2021-03-23 | 2021-04-02 | 2021-04-09 | 2021-04-13 | 2021-05-19 | 2021-06-03 | 2021-06-15 | 2021-06-18 | 2021-07-01 |  | 2021-07-09 | 2021-08-10
2021-04-12 | 2021-04-26 | 2021-05-06 | 2021-05-13 | 2021-05-17 | 2021-06-23 | 2021-07-08 | 2021-07-20 | 2021-07-23 | 2021-08-05 |  | 2021-08-12 | 2021-09-14
2021-05-07 | 2021-05-21 | 2021-06-03 | 2021-06-10 | 2021-06-14 | 2021-07-21 | 2021-08-04 | 2021-08-16 | 2021-08-19 | 2021-09-01 |  | 2021-09-09 | 2021-10-12
2021-06-07 | 2021-06-21 | 2021-07-01 | 2021-07-09 | 2021-07-13 | 2021-08-18 | 2021-09-01 | 2021-09-14 | 2021-09-17 | 2021-09-30 |  | 2021-10-07 | 2021-11-09
2021-06-30 | 2021-07-15 | 2021-07-27 | 2021-08-03 | 2021-08-05 | 2021-09-13 | 2021-09-27 | 2021-10-07 | 2021-10-13 | 2021-10-26 |  | 2021-11-02 | 2021-12-07
2021-06-30: 68 END; 2021-08-03: 71, 79 BEG; 2021-08-05: 72 BEG; 2021-10-13: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2021-10-26: 63 END |  | 80 BEG | 80 END
2021-06-30: 70 END; 2021-08-03: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2021-10-26: 71 END |  | 72 END
2021-06-30: 71X; 2021-10-26: 72X | 6
2021-06-30: 71C END; 2021-10-26: 21A,B END | 9
2021-10-13: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2021-10-26: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2022
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2022
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2021-08-04 | 2021-08-18 | 2021-08-30 | 2021-09-07 | 2021-09-09 | 2021-10-18 | 2021-11-01 | 2021-11-12 | 2021-11-17 | 2021-12-02 |  | 2021-12-09 | 2022-01-11
2021-08-30 | 2021-09-14 | 2021-09-24 | 2021-10-01 | 2021-10-05 | 2021-11-12 | 2021-11-30 | 2021-12-10 | 2021-12-15 | 2021-12-29 |  | 2022-01-05 | 2022-02-08
2021-09-27 | 2021-10-12 | 2021-10-22 | 2021-10-29 | 2021-11-02 | 2021-12-13 | 2021-12-28 | 2022-01-07 | 2022-01-12 | 2022-01-27 |  | 2022-02-03 | 2022-03-08
2021-11-02 | 2021-11-17 | 2021-12-01 | 2021-12-08 | 2021-12-10 | 2022-01-20 | 2022-02-03 | 2022-02-15 | 2022-02-18 | 2022-03-04 |  | 2022-03-11 | 2022-04-12
2021-12-03 | 2021-12-17 | 2021-12-30 | 2022-01-06 | 2022-01-10 | 2022-02-17 | 2022-03-04 | 2022-03-16 | 2022-03-21 | 2022-04-01 |  | 2022-04-08 | 2022-05-10
2021-12-31 | 2022-01-18 | 2022-01-28 | 2022-02-04 | 2022-02-08 | 2022-03-17 | 2022-03-31 | 2022-04-12 | 2022-04-15 | 2022-04-28 |  | 2022-05-05 | 2022-06-07
2022-02-07 | 2022-02-22 | 2022-03-04 | 2022-03-11 | 2022-03-15 | 2022-04-20 | 2022-05-04 | 2022-05-16 | 2022-05-19 | 2022-06-02 |  | 2022-06-09 | 2022-07-12
2022-03-08 | 2022-03-22 | 2022-04-01 | 2022-04-08 | 2022-04-12 | 2022-05-18 | 2022-06-02 | 2022-06-14 | 2022-06-17 | 2022-06-30 |  | 2022-07-08 | 2022-08-09
2022-04-11 | 2022-04-25 | 2022-05-05 | 2022-05-12 | 2022-05-16 | 2022-06-22 | 2022-07-07 | 2022-07-19 | 2022-07-22 | 2022-08-04 |  | 2022-08-11 | 2022-09-13
2022-05-06 | 2022-05-20 | 2022-06-02 | 2022-06-09 | 2022-06-13 | 2022-07-20 | 2022-08-03 | 2022-08-15 | 2022-08-18 | 2022-08-31 |  | 2022-09-08 | 2022-10-11
2022-06-07 | 2022-06-21 | 2022-07-01 | 2022-07-11 | 2022-07-13 | 2022-08-18 | 2022-09-01 | 2022-09-14 | 2022-09-19 | 2022-09-30 |  | 2022-10-07 | 2022-11-09
2022-06-29 | 2022-07-14 | 2022-07-26 | 2022-08-02 | 2022-08-04 | 2022-09-12 | 2022-09-26 | 2022-10-06 | 2022-10-12 | 2022-10-25 |  | 2022-11-01 | 2022-12-06
-11
2022-06-29: 68 END; 2022-08-02: 71, 79 BEG; 2022-08-04: 72 BEG; 2022-10-12: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2022-10-25: 63 END |  | 80 BEG | 80 END
2022-06-29: 70 END; 2022-08-02: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2022-10-25: 71 END |  | 72 END
2022-06-29: 71X; 2022-10-25: 72X | 6
2022-06-29: 71C END; 2022-10-25: 21A,B END | 9
2022-10-12: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2022-10-25: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2023
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2023
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2022-08-03 | 2022-08-17 | 2022-08-29 | 2022-09-06 | 2022-09-08 | 2022-10-17 | 2022-10-31 | 2022-11-10 | 2022-11-16 | 2022-12-01 |  | 2022-12-08 | 2023-01-10
2022-09-06 | 2022-09-20 | 2022-09-30 | 2022-10-07 | 2022-10-12 | 2022-11-18 | 2022-12-06 | 2022-12-16 | 2022-12-21 | 2023-01-04 |  | 2023-01-11 | 2023-02-14
2022-10-03 | 2022-10-18 | 2022-10-28 | 2022-11-04 | 2022-11-08 | 2022-12-19 | 2023-01-03 | 2023-01-17 | 2023-01-20 | 2023-02-02 |  | 2023-02-09 | 2023-03-14
2022-11-01 | 2022-11-16 | 2022-11-30 | 2022-12-07 | 2022-12-09 | 2023-01-19 | 2023-02-02 | 2023-02-14 | 2023-02-17 | 2023-03-03 |  | 2023-03-10 | 2023-04-11
2022-12-02 | 2022-12-16 | 2022-12-28 | 2023-01-05 | 2023-01-09 | 2023-02-16 | 2023-03-03 | 2023-03-15 | 2023-03-20 | 2023-03-31 |  | 2023-04-07 | 2023-05-09
2022-12-29 | 2023-01-17 | 2023-01-27 | 2023-02-03 | 2023-02-07 | 2023-03-16 | 2023-03-30 | 2023-04-11 | 2023-04-14 | 2023-04-27 |  | 2023-05-04 | 2023-06-06
2023-02-06 | 2023-02-21 | 2023-03-03 | 2023-03-10 | 2023-03-14 | 2023-04-19 | 2023-05-03 | 2023-05-15 | 2023-05-18 | 2023-06-01 |  | 2023-06-08 | 2023-07-11
2023-03-07 | 2023-03-21 | 2023-03-31 | 2023-04-07 | 2023-04-11 | 2023-05-17 | 2023-06-01 | 2023-06-13 | 2023-06-16 | 2023-06-29 |  | 2023-07-07 | 2023-08-08
2023-04-10 | 2023-04-24 | 2023-05-04 | 2023-05-11 | 2023-05-15 | 2023-06-21 | 2023-07-06 | 2023-07-18 | 2023-07-21 | 2023-08-03 |  | 2023-08-10 | 2023-09-12
2023-05-05 | 2023-05-19 | 2023-06-01 | 2023-06-08 | 2023-06-12 | 2023-07-19 | 2023-08-02 | 2023-08-14 | 2023-08-17 | 2023-08-30 |  | 2023-09-07 | 2023-10-10
2023-06-07 | 2023-06-21 | 2023-07-03 | 2023-07-11 | 2023-07-13 | 2023-08-18 | 2023-09-01 | 2023-09-14 | 2023-09-19 | 2023-10-02 |  | 2023-10-10 | 2023-11-09
2023-06-28 | 2023-07-13 | 2023-07-25 | 2023-08-01 | 2023-08-03 | 2023-09-11 | 2023-09-25 | 2023-10-05 | 2023-10-11 | 2023-10-24 |  | 2023-10-31 | 2023-12-05
2023-06-28: 68 END; 2023-08-01: 71, 79 BEG; 2023-08-03: 72 BEG; 2023-10-11: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2023-10-24: 63 END |  | 80 BEG | 80 END
2023-06-28: 70 END; 2023-08-01: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2023-10-24: 71 END |  | 72 END
2023-06-28: 71X; 2023-10-24: 72X | 6
2023-06-28: 71C END; 2023-10-24: 21A,B END | 9
2023-10-11: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2023-10-24: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2024
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2024
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2023-08-01 | 2023-08-15 | 2023-08-25 | 2023-09-01 | 2023-09-06 | 2023-10-13 | 2023-10-27 | 2023-11-08 | 2023-11-14 | 2023-11-29 |  | 2023-12-06 | 2024-01-09
2023-09-01 | 2023-09-18 | 2023-09-28 | 2023-10-05 | 2023-10-10 | 2023-11-16 | 2023-12-04 | 2023-12-14 | 2023-12-19 | 2024-01-03 |  | 2024-01-10 | 2024-02-13
2023-09-29 | 2023-10-16 | 2023-10-26 | 2023-11-02 | 2023-11-06 | 2023-12-15 | 2024-01-02 | 2024-01-16 | 2024-01-19 | 2024-02-01 |  | 2024-02-08 | 2024-03-12
2023-10-30 | 2023-11-14 | 2023-11-28 | 2023-12-05 | 2023-12-07 | 2024-01-18 | 2024-02-01 | 2024-02-13 | 2024-02-16 | 2024-03-01 |  | 2024-03-08 | 2024-04-09
2023-12-07 | 2023-12-21 | 2024-01-04 | 2024-01-11 | 2024-01-17 | 2024-02-23 | 2024-03-08 | 2024-03-20 | 2024-03-25 | 2024-04-05 |  | 2024-04-12 | 2024-05-14
2024-01-05 | 2024-01-23 | 2024-02-02 | 2024-02-09 | 2024-02-13 | 2024-03-21 | 2024-04-04 | 2024-04-16 | 2024-04-19 | 2024-05-02 |  | 2024-05-09 | 2024-06-11
2024-02-05 | 2024-02-20 | 2024-03-01 | 2024-03-08 | 2024-03-12 | 2024-04-17 | 2024-05-01 | 2024-05-13 | 2024-05-16 | 2024-05-30 |  | 2024-06-06 | 2024-07-09
2024-03-12 | 2024-03-26 | 2024-04-05 | 2024-04-12 | 2024-04-16 | 2024-05-22 | 2024-06-06 | 2024-06-18 | 2024-06-21 | 2024-07-05 |  | 2024-07-12 | 2024-08-13
2024-04-08 | 2024-04-22 | 2024-05-02 | 2024-05-09 | 2024-05-13 | 2024-06-19 | 2024-07-03 | 2024-07-16 | 2024-07-19 | 2024-08-01 |  | 2024-08-08 | 2024-09-10
2024-05-06 | 2024-05-20 | 2024-05-31 | 2024-06-07 | 2024-06-11 | 2024-07-18 | 2024-08-01 | 2024-08-13 | 2024-08-16 | 2024-08-29 |  | 2024-09-06 | 2024-10-08
2024-06-07 | 2024-06-21 | 2024-07-03 | 2024-07-11 | 2024-07-15 | 2024-08-20 | 2024-09-04 | 2024-09-16 | 2024-09-19 | 2024-10-02 |  | 2024-10-09 | 2024-11-12
2024-06-26 | 2024-07-11 | 2024-07-23 | 2024-07-30 | 2024-08-01 | 2024-09-09 | 2024-09-23 | 2024-10-03 | 2024-10-08 | 2024-10-22 |  | 2024-10-29 | 2024-12-03
-3
2024-06-26: 68 END; 2024-07-30: 71, 79 BEG; 2024-08-01: 72 BEG; 2024-10-08: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2024-10-22: 63 END |  | 80 BEG | 80 END
2024-06-26: 70 END; 2024-07-30: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2024-10-22: 71 END |  | 72 END
2024-06-26: 71X; 2024-10-22: 72X | 6
2024-06-26: 71C END; 2024-10-22: 21A,B END | 9
2024-10-08: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2024-10-22: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2025
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2025
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2024-08-06 | 2024-08-20 | 2024-08-30 | 2024-09-09 | 2024-09-11 | 2024-10-18 | 2024-11-01 | 2024-11-14 | 2024-11-19 | 2024-12-04 |  | 2024-12-11 | 2025-01-14
2024-08-30 | 2024-09-16 | 2024-09-26 | 2024-10-03 | 2024-10-07 | 2024-11-14 | 2024-12-02 | 2024-12-12 | 2024-12-17 | 2024-12-31 |  | 2025-01-08 | 2025-02-11
2024-09-27 | 2024-10-11 | 2024-10-24 | 2024-10-31 | 2024-11-04 | 2024-12-13 | 2024-12-30 | 2025-01-10 | 2025-01-15 | 2025-01-30 |  | 2025-02-06 | 2025-03-11
2024-10-28 | 2024-11-12 | 2024-11-22 | 2024-12-03 | 2024-12-05 | 2025-01-14 | 2025-01-30 | 2025-02-11 | 2025-02-14 | 2025-02-28 |  | 2025-03-07 | 2025-04-08
2024-12-05 | 2024-12-19 | 2025-01-02 | 2025-01-09 | 2025-01-13 | 2025-02-21 | 2025-03-07 | 2025-03-19 | 2025-03-24 | 2025-04-04 |  | 2025-04-11 | 2025-05-13
2025-01-03 | 2025-01-21 | 2025-01-31 | 2025-02-07 | 2025-02-11 | 2025-03-20 | 2025-04-03 | 2025-04-15 | 2025-04-18 | 2025-05-01 |  | 2025-05-08 | 2025-06-10
2025-02-03 | 2025-02-18 | 2025-02-28 | 2025-03-07 | 2025-03-11 | 2025-04-16 | 2025-04-30 | 2025-05-12 | 2025-05-15 | 2025-05-29 |  | 2025-06-05 | 2025-07-08
2025-03-11 | 2025-03-25 | 2025-04-04 | 2025-04-11 | 2025-04-15 | 2025-05-21 | 2025-06-05 | 2025-06-17 | 2025-06-20 | 2025-07-03 |  | 2025-07-11 | 2025-08-12
2025-04-07 | 2025-04-21 | 2025-05-01 | 2025-05-08 | 2025-05-12 | 2025-06-18 | 2025-07-02 | 2025-07-15 | 2025-07-18 | 2025-07-31 |  | 2025-08-07 | 2025-09-09
2025-05-09 | 2025-05-23 | 2025-06-05 | 2025-06-12 | 2025-06-16 | 2025-07-23 | 2025-08-06 | 2025-08-18 | 2025-08-21 | 2025-09-04 |  | 2025-09-11 | 2025-10-14
2025-06-09 | 2025-06-23 | 2025-07-03 | 2025-07-11 | 2025-07-15 | 2025-08-20 | 2025-09-04 | 2025-09-16 | 2025-09-19 | 2025-10-02 |  | 2025-10-09 | 2025-11-12
2025-07-02 | 2025-07-17 | 2025-07-29 | 2025-08-05 | 2025-08-07 | 2025-09-15 | 2025-09-29 | 2025-10-09 | 2025-10-15 | 2025-10-28 |  | 2025-11-04 | 2025-12-09
-5
2025-07-02: 68 END; 2025-08-05: 71, 79 BEG; 2025-08-07: 72 BEG; 2025-10-15: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2025-10-28: 63 END |  | 80 BEG | 80 END
2025-07-02: 70 END; 2025-08-05: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2025-10-28: 71 END |  | 72 END
2025-07-02: 71X; 2025-10-28: 72X | 6
2025-07-02: 71C END; 2025-10-28: 21A,B END | 9
2025-10-15: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2025-10-28: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2026
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2026
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2025-08-05 | 2025-08-19 | 2025-08-29 | 2025-09-08 | 2025-09-10 | 2025-10-17 | 2025-10-31 | 2025-11-13 | 2025-11-18 | 2025-12-03 |  | 2025-12-10 | 2026-01-13
2025-08-29 | 2025-09-15 | 2025-09-25 | 2025-10-02 | 2025-10-06 | 2025-11-13 | 2025-12-01 | 2025-12-11 | 2025-12-16 | 2025-12-30 |  | 2026-01-07 | 2026-02-10
2025-09-26 | 2025-10-10 | 2025-10-23 | 2025-10-30 | 2025-11-03 | 2025-12-12 | 2025-12-29 | 2026-01-09 | 2026-01-14 | 2026-01-29 |  | 2026-02-05 | 2026-03-10
2025-11-03 | 2025-11-18 | 2025-12-02 | 2025-12-09 | 2025-12-11 | 2026-01-22 | 2026-02-05 | 2026-02-18 | 2026-02-23 | 2026-03-06 |  | 2026-03-13 | 2026-04-14
2025-12-04 | 2025-12-18 | 2025-12-31 | 2026-01-08 | 2026-01-12 | 2026-02-20 | 2026-03-06 | 2026-03-18 | 2026-03-23 | 2026-04-03 |  | 2026-04-10 | 2026-05-12
2026-01-02 | 2026-01-20 | 2026-01-30 | 2026-02-06 | 2026-02-10 | 2026-03-19 | 2026-04-02 | 2026-04-14 | 2026-04-17 | 2026-04-30 |  | 2026-05-07 | 2026-06-09
2026-02-09 | 2026-02-24 | 2026-03-06 | 2026-03-13 | 2026-03-17 | 2026-04-22 | 2026-05-06 | 2026-05-18 | 2026-05-21 | 2026-06-04 |  | 2026-06-11 | 2026-07-14
2026-03-10 | 2026-03-24 | 2026-04-03 | 2026-04-10 | 2026-04-14 | 2026-05-20 | 2026-06-04 | 2026-06-16 | 2026-06-19 | 2026-07-02 |  | 2026-07-10 | 2026-08-11
2026-04-06 | 2026-04-20 | 2026-04-30 | 2026-05-07 | 2026-05-11 | 2026-06-17 | 2026-07-01 | 2026-07-14 | 2026-07-17 | 2026-07-30 |  | 2026-08-06 | 2026-09-08
2026-05-08 | 2026-05-22 | 2026-06-04 | 2026-06-11 | 2026-06-15 | 2026-07-22 | 2026-08-05 | 2026-08-17 | 2026-08-20 | 2026-09-02 |  | 2026-09-10 | 2026-10-13
2026-06-08 | 2026-06-22 | 2026-07-02 | 2026-07-10 | 2026-07-14 | 2026-08-19 | 2026-09-02 | 2026-09-15 | 2026-09-18 | 2026-10-01 |  | 2026-10-08 | 2026-11-10
2026-07-01 | 2026-07-16 | 2026-07-28 | 2026-08-04 | 2026-08-06 | 2026-09-14 | 2026-09-28 | 2026-10-08 | 2026-10-14 | 2026-10-27 |  | 2026-11-03 | 2026-12-08
| -19 | -9 | -2
2026-07-01: 68 END; 2026-08-04: 71, 79 BEG; 2026-08-06: 72 BEG; 2026-10-14: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2026-10-27: 63 END |  | 80 BEG | 80 END
2026-07-01: 70 END; 2026-08-04: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2026-10-27: 71 END |  | 72 END
2026-07-01: 71X; 2026-10-27: 72X | 6
2026-07-01: 71C END; 2026-10-27: 21A,B END | 9
2026-10-14: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2026-10-27: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2027
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2027
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2026-08-04 | 2026-08-18 | 2026-08-28 | 2026-09-04 | 2026-09-09 | 2026-10-16 | 2026-10-30 | 2026-11-12 | 2026-11-17 | 2026-12-02 |  | 2026-12-09 | 2027-01-12
2026-08-28 | 2026-09-14 | 2026-09-24 | 2026-10-01 | 2026-10-05 | 2026-11-12 | 2026-11-30 | 2026-12-10 | 2026-12-15 | 2026-12-29 |  | 2027-01-06 | 2027-02-09
2026-09-25 | 2026-10-09 | 2026-10-22 | 2026-10-29 | 2026-11-02 | 2026-12-11 | 2026-12-28 | 2027-01-08 | 2027-01-13 | 2027-01-28 |  | 2027-02-04 | 2027-03-09
2026-11-02 | 2026-11-17 | 2026-12-01 | 2026-12-08 | 2026-12-10 | 2027-01-21 | 2027-02-04 | 2027-02-17 | 2027-02-22 | 2027-03-05 |  | 2027-03-12 | 2027-04-13
2026-12-03 | 2026-12-17 | 2026-12-30 | 2027-01-07 | 2027-01-11 | 2027-02-19 | 2027-03-05 | 2027-03-17 | 2027-03-22 | 2027-04-02 |  | 2027-04-09 | 2027-05-11
2026-12-31 | 2027-01-19 | 2027-01-29 | 2027-02-05 | 2027-02-09 | 2027-03-18 | 2027-04-01 | 2027-04-13 | 2027-04-16 | 2027-04-29 |  | 2027-05-06 | 2027-06-08
2027-02-08 | 2027-02-23 | 2027-03-05 | 2027-03-12 | 2027-03-16 | 2027-04-21 | 2027-05-05 | 2027-05-17 | 2027-05-20 | 2027-06-03 |  | 2027-06-10 | 2027-07-13
2027-03-09 | 2027-03-23 | 2027-04-02 | 2027-04-09 | 2027-04-13 | 2027-05-19 | 2027-06-03 | 2027-06-15 | 2027-06-18 | 2027-07-01 |  | 2027-07-09 | 2027-08-10
2027-04-12 | 2027-04-26 | 2027-05-06 | 2027-05-13 | 2027-05-17 | 2027-06-23 | 2027-07-08 | 2027-07-20 | 2027-07-23 | 2027-08-05 |  | 2027-08-12 | 2027-09-14
2027-05-07 | 2027-05-21 | 2027-06-03 | 2027-06-10 | 2027-06-14 | 2027-07-21 | 2027-08-04 | 2027-08-16 | 2027-08-19 | 2027-09-01 |  | 2027-09-09 | 2027-10-12
2027-06-07 | 2027-06-21 | 2027-07-01 | 2027-07-09 | 2027-07-13 | 2027-08-18 | 2027-09-01 | 2027-09-14 | 2027-09-17 | 2027-09-30 |  | 2027-10-07 | 2027-11-09
2027-07-08 | 2027-07-22 | 2027-08-03 | 2027-08-10 | 2027-08-12 | 2027-09-20 | 2027-10-04 | 2027-10-15 | 2027-10-20 | 2027-11-02 |  | 2027-11-09 | 2027-12-14
| -19 | -9 | -2
2027-07-08: 68 END; 2027-08-10: 71, 79 BEG; 2027-08-12: 72 BEG; 2027-10-20: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2027-11-02: 63 END |  | 80 BEG | 80 END
2027-07-08: 70 END; 2027-08-10: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2027-11-02: 71 END |  | 72 END
2027-07-08: 71X; 2027-11-02: 72X | 6
2027-07-08: 71C END; 2027-11-02: 21A,B END | 9
2027-10-20: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2027-11-02: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2028
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2028
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2027-08-03 | 2027-08-17 | 2027-08-27 | 2027-09-03 | 2027-09-08 | 2027-10-15 | 2027-10-29 | 2027-11-10 | 2027-11-16 | 2027-12-01 |  | 2027-12-08 | 2028-01-11
2027-08-27 | 2027-09-13 | 2027-09-23 | 2027-09-30 | 2027-10-04 | 2027-11-10 | 2027-11-29 | 2027-12-09 | 2027-12-14 | 2027-12-28 |  | 2028-01-05 | 2028-02-08
2027-10-01 | 2027-10-18 | 2027-10-28 | 2027-11-04 | 2027-11-08 | 2027-12-17 | 2028-01-04 | 2028-01-18 | 2028-01-21 | 2028-02-03 |  | 2028-02-10 | 2028-03-14
2027-11-01 | 2027-11-16 | 2027-11-30 | 2027-12-07 | 2027-12-09 | 2028-01-20 | 2028-02-03 | 2028-02-15 | 2028-02-18 | 2028-03-03 |  | 2028-03-10 | 2028-04-11
2027-12-02 | 2027-12-16 | 2027-12-29 | 2028-01-06 | 2028-01-10 | 2028-02-17 | 2028-03-03 | 2028-03-15 | 2028-03-20 | 2028-03-31 |  | 2028-04-07 | 2028-05-09
2028-01-07 | 2028-01-25 | 2028-02-04 | 2028-02-11 | 2028-02-15 | 2028-03-23 | 2028-04-06 | 2028-04-18 | 2028-04-21 | 2028-05-04 |  | 2028-05-11 | 2028-06-13
2028-02-07 | 2028-02-22 | 2028-03-03 | 2028-03-10 | 2028-03-14 | 2028-04-19 | 2028-05-03 | 2028-05-15 | 2028-05-18 | 2028-06-01 |  | 2028-06-08 | 2028-07-11
2028-03-07 | 2028-03-21 | 2028-03-31 | 2028-04-07 | 2028-04-11 | 2028-05-17 | 2028-06-01 | 2028-06-13 | 2028-06-16 | 2028-06-29 |  | 2028-07-07 | 2028-08-08
2028-04-10 | 2028-04-24 | 2028-05-04 | 2028-05-11 | 2028-05-15 | 2028-06-21 | 2028-07-06 | 2028-07-18 | 2028-07-21 | 2028-08-03 |  | 2028-08-10 | 2028-09-12
2028-05-05 | 2028-05-19 | 2028-06-01 | 2028-06-08 | 2028-06-12 | 2028-07-19 | 2028-08-02 | 2028-08-14 | 2028-08-17 | 2028-08-30 |  | 2028-09-07 | 2028-10-10
2028-06-09 | 2028-06-23 | 2028-07-06 | 2028-07-13 | 2028-07-17 | 2028-08-22 | 2028-09-06 | 2028-09-18 | 2028-09-21 | 2028-10-04 |  | 2028-10-12 | 2028-11-14
2028-07-06 | 2028-07-20 | 2028-08-01 | 2028-08-08 | 2028-08-10 | 2028-09-18 | 2028-10-02 | 2028-10-13 | 2028-10-18 | 2028-10-31 |  | 2028-11-07 | 2028-12-12
| -19 | -9 | -2
2028-07-06: 68 END; 2028-08-08: 71, 79 BEG; 2028-08-10: 72 BEG; 2028-10-18: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2028-10-31: 63 END |  | 80 BEG | 80 END
2028-07-06: 70 END; 2028-08-08: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2028-10-31: 71 END |  | 72 END
2028-07-06: 71X; 2028-10-31: 72X | 6
2028-07-06: 71C END; 2028-10-31: 21A,B END | 9
2028-10-18: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2028-10-31: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2029
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2029
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2028-08-02 | 2028-08-16 | 2028-08-28 | 2028-09-05 | 2028-09-07 | 2028-10-16 | 2028-10-30 | 2028-11-09 | 2028-11-15 | 2028-11-30 |  | 2028-12-07 | 2029-01-09
2028-09-05 | 2028-09-19 | 2028-09-29 | 2028-10-06 | 2028-10-11 | 2028-11-17 | 2028-12-05 | 2028-12-15 | 2028-12-20 | 2029-01-03 |  | 2029-01-10 | 2029-02-13
2028-10-02 | 2028-10-17 | 2028-10-27 | 2028-11-03 | 2028-11-07 | 2028-12-18 | 2029-01-02 | 2029-01-16 | 2029-01-19 | 2029-02-01 |  | 2029-02-08 | 2029-03-13
2028-10-31 | 2028-11-15 | 2028-11-29 | 2028-12-06 | 2028-12-08 | 2029-01-18 | 2029-02-01 | 2029-02-13 | 2029-02-16 | 2029-03-02 |  | 2029-03-09 | 2029-04-10
2028-12-01 | 2028-12-15 | 2028-12-28 | 2029-01-04 | 2029-01-08 | 2029-02-15 | 2029-03-02 | 2029-03-14 | 2029-03-19 | 2029-03-30 |  | 2029-04-06 | 2029-05-08
2029-01-05 | 2029-01-23 | 2029-02-02 | 2029-02-09 | 2029-02-13 | 2029-03-22 | 2029-04-05 | 2029-04-17 | 2029-04-20 | 2029-05-03 |  | 2029-05-10 | 2029-06-12
2029-02-05 | 2029-02-20 | 2029-03-02 | 2029-03-09 | 2029-03-13 | 2029-04-18 | 2029-05-02 | 2029-05-14 | 2029-05-17 | 2029-05-31 |  | 2029-06-07 | 2029-07-10
2029-03-13 | 2029-03-27 | 2029-04-06 | 2029-04-13 | 2029-04-17 | 2029-05-23 | 2029-06-07 | 2029-06-19 | 2029-06-22 | 2029-07-06 |  | 2029-07-13 | 2029-08-14
2029-04-09 | 2029-04-23 | 2029-05-03 | 2029-05-10 | 2029-05-14 | 2029-06-20 | 2029-07-05 | 2029-07-17 | 2029-07-20 | 2029-08-02 |  | 2029-08-09 | 2029-09-11
2029-05-04 | 2029-05-18 | 2029-05-31 | 2029-06-07 | 2029-06-11 | 2029-07-18 | 2029-08-01 | 2029-08-13 | 2029-08-16 | 2029-08-29 |  | 2029-09-06 | 2029-10-09
2029-06-08 | 2029-06-22 | 2029-07-05 | 2029-07-12 | 2029-07-16 | 2029-08-21 | 2029-09-05 | 2029-09-17 | 2029-09-20 | 2029-10-03 |  | 2029-10-11 | 2029-11-13
2029-07-05 | 2029-07-19 | 2029-07-31 | 2029-08-07 | 2029-08-09 | 2029-09-17 | 2029-10-01 | 2029-10-12 | 2029-10-17 | 2029-10-30 |  | 2029-11-06 | 2029-12-11
| -19 | -9 | -2 |  | -12
2029-07-05: 68 END; 2029-08-07: 71, 79 BEG; 2029-08-09: 72 BEG; 2029-10-17: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2029-10-30: 63 END |  | 80 BEG | 80 END
2029-07-05: 70 END; 2029-08-07: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2029-10-30: 71 END |  | 72 END
2029-07-05: 71X; 2029-10-30: 72X | 6
2029-07-05: 71C END; 2029-10-30: 21A,B END | 9
2029-10-17: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2029-10-30: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2030
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2030
Falcon Location: Current Drawings | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2029-07-31 | 2029-08-14 | 2029-08-24 | 2029-08-31 | 2029-09-05 | 2029-10-12 | 2029-10-26 | 2029-11-07 | 2029-11-13 | 2029-11-28 |  | 2029-12-05 | 2030-01-08
2029-08-31 | 2029-09-17 | 2029-09-27 | 2029-10-04 | 2029-10-09 | 2029-11-15 | 2029-12-03 | 2029-12-13 | 2029-12-18 | 2030-01-02 |  | 2030-01-09 | 2030-02-12
2029-09-28 | 2029-10-15 | 2029-10-25 | 2029-11-01 | 2029-11-05 | 2029-12-14 | 2030-01-01 | 2030-01-11 | 2030-01-16 | 2030-01-31 |  | 2030-02-07 | 2030-03-12
2029-10-29 | 2029-11-13 | 2029-11-27 | 2029-12-04 | 2029-12-06 | 2030-01-15 | 2030-01-31 | 2030-02-12 | 2030-02-15 | 2030-03-01 |  | 2030-03-08 | 2030-04-09
2029-12-06 | 2029-12-20 | 2030-01-03 | 2030-01-10 | 2030-01-14 | 2030-02-22 | 2030-03-08 | 2030-03-20 | 2030-03-25 | 2030-04-05 |  | 2030-04-12 | 2030-05-14
2030-01-04 | 2030-01-22 | 2030-02-01 | 2030-02-08 | 2030-02-12 | 2030-03-21 | 2030-04-04 | 2030-04-16 | 2030-04-19 | 2030-05-02 |  | 2030-05-09 | 2030-06-11
2030-02-04 | 2030-02-19 | 2030-03-01 | 2030-03-08 | 2030-03-12 | 2030-04-17 | 2030-05-01 | 2030-05-13 | 2030-05-16 | 2030-05-30 |  | 2030-06-06 | 2030-07-09
2030-03-12 | 2030-03-26 | 2030-04-05 | 2030-04-12 | 2030-04-16 | 2030-05-22 | 2030-06-06 | 2030-06-18 | 2030-06-21 | 2030-07-05 |  | 2030-07-12 | 2030-08-13
2030-04-08 | 2030-04-22 | 2030-05-02 | 2030-05-09 | 2030-05-13 | 2030-06-19 | 2030-07-03 | 2030-07-16 | 2030-07-19 | 2030-08-01 |  | 2030-08-08 | 2030-09-10
2030-05-06 | 2030-05-20 | 2030-05-31 | 2030-06-07 | 2030-06-11 | 2030-07-18 | 2030-08-01 | 2030-08-13 | 2030-08-16 | 2030-08-29 |  | 2030-09-06 | 2030-10-08
2030-06-07 | 2030-06-21 | 2030-07-03 | 2030-07-11 | 2030-07-15 | 2030-08-20 | 2030-09-04 | 2030-09-16 | 2030-09-19 | 2030-10-02 |  | 2030-10-09 | 2030-11-12
2030-07-03 | 2030-07-18 | 2030-07-30 | 2030-08-06 | 2030-08-08 | 2030-09-16 | 2030-09-30 | 2030-10-10 | 2030-10-16 | 2030-10-29 |  | 2030-11-05 | 2030-12-10
| -19 | -9 | -2
2030-07-03: 68 END; 2030-08-06: 71, 79 BEG; 2030-08-08: 72 BEG; 2030-10-16: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2030-10-29: 63 END |  | 80 BEG | 80 END
2030-07-03: 70 END; 2030-08-06: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2030-10-29: 71 END |  | 72 END
2030-07-03: 71X; 2030-10-29: 72X | 6
2030-07-03: 71C END; 2030-10-29: 21A,B END | 9
2030-10-16: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2030-10-29: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.

## RAAP 2031
REV. 9/1/20
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 2 CONSTRUCTION AND MAINTENANCE PROJECTS 2031
REV. 9/1/20 | Falcon Location: Plan File Room | Falcon Location: Plan File Room | [5 empty] | Falcon Location: Plan File Room
ALL PLANS REVIEWED AND PRE-ADVERTISEMENT CONFERENCE HELD | PLAN COORDINATION REVIEW: PLAN REVISIONS COMPLETE AND PLAN COORDINATION REVIEW BEGINS | PLAN COORDINATION REVIEW COMPLETE AND PROJECT MANAGER CERTIFICATION BEGINS | PROJECT MANAGER CERTIFICATION ENDS AND PLAN COORDINATION PROCESSING BEGINS --INITIATE ENVI. CERT. & VERIFICATION | PLAN COORDINATION PROCESSING ENDS AND CONTRACT DEVELOPMENT BEGINS-- | BIDDABILITY REVIEW |  |  | ADVERTISEMENT SUBMISSION: COMPLETE PLAN ASSEMBLY TO PLAN COORDINATION WITH ADV. REQUESTS | ADVERTISEMENT SUBMISSION TO SCHEDULING & CONTRACT ENGR. AND PRINT REPRODUCTION FOR PS&E BEGINS | RIGHT OF WAY CERTIFICATION | FINAL PS&E TO FHWA | ADVERTISEMENT
[5 empty] | CONTRACT DEVELOPMENT COMPLETE ENVI. CERT. & VERIFICATION COMPLETE AND TITLE SHEET SIGNED | END BIDDIBILITY REVIEW BY DISTRICT CONSTRUCTION ENGINEER STAFF | REVISIONS TO CONTRACT DOCUMENTS PER BIDDIBILITY COMMENTS ENDS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12
2030-08-06 | 2030-08-20 | 2030-08-30 | 2030-09-09 | 2030-09-11 | 2030-10-18 | 2030-11-01 | 2030-11-14 | 2030-11-19 | 2030-12-04 |  | 2030-12-11 | 2031-01-14
2030-08-30 | 2030-09-16 | 2030-09-26 | 2030-10-03 | 2030-10-07 | 2030-11-14 | 2030-12-02 | 2030-12-12 | 2030-12-17 | 2031-01-01 |  | 2031-01-08 | 2031-02-11
2030-09-27 | 2030-10-11 | 2030-10-24 | 2030-10-31 | 2030-11-04 | 2030-12-13 | 2030-12-30 | 2031-01-10 | 2031-01-15 | 2031-01-30 |  | 2031-02-06 | 2031-03-11
2030-10-28 | 2030-11-12 | 2030-11-22 | 2030-12-03 | 2030-12-05 | 2031-01-14 | 2031-01-30 | 2031-02-11 | 2031-02-14 | 2031-02-28 |  | 2031-03-07 | 2031-04-08
2030-12-05 | 2030-12-19 | 2031-01-02 | 2031-01-09 | 2031-01-13 | 2031-02-21 | 2031-03-07 | 2031-03-19 | 2031-03-24 | 2031-04-04 |  | 2031-04-11 | 2031-05-13
2031-01-03 | 2031-01-21 | 2031-01-31 | 2031-02-07 | 2031-02-11 | 2031-03-20 | 2031-04-03 | 2031-04-15 | 2031-04-18 | 2031-05-01 |  | 2031-05-08 | 2031-06-10
2031-02-03 | 2031-02-18 | 2031-02-28 | 2031-03-07 | 2031-03-11 | 2031-04-16 | 2031-04-30 | 2031-05-12 | 2031-05-15 | 2031-05-29 |  | 2031-06-05 | 2031-07-08
2031-03-11 | 2031-03-25 | 2031-04-04 | 2031-04-11 | 2031-04-15 | 2031-05-21 | 2031-06-05 | 2031-06-17 | 2031-06-20 | 2031-07-03 |  | 2031-07-11 | 2031-08-12
2031-04-07 | 2031-04-21 | 2031-05-01 | 2031-05-08 | 2031-05-12 | 2031-06-18 | 2031-07-02 | 2031-07-15 | 2031-07-18 | 2031-07-31 |  | 2031-08-07 | 2031-09-09
2031-05-09 | 2031-05-23 | 2031-06-05 | 2031-06-12 | 2031-06-16 | 2031-07-23 | 2031-08-06 | 2031-08-18 | 2031-08-21 | 2031-09-04 |  | 2031-09-11 | 2031-10-14
2031-06-06 | 2031-06-20 | 2031-07-02 | 2031-07-10 | 2031-07-14 | 2031-08-19 | 2031-09-03 | 2031-09-15 | 2031-09-18 | 2031-10-01 |  | 2031-10-08 | 2031-11-10
2031-07-02 | 2031-07-17 | 2031-07-29 | 2031-08-05 | 2031-08-07 | 2031-09-15 | 2031-09-29 | 2031-10-09 | 2031-10-15 | 2031-10-28 |  | 2031-11-04 | 2031-12-09
| -19 | -9 | -2
2031-07-02: 68 END; 2031-08-05: 71, 79 BEG; 2031-08-07: 72 BEG; 2031-10-15: NO CHANGES TO THE PLANS OR CONTRACT DOCUMENTS AFTER THIS DATE; 2031-10-28: 63 END |  | 80 BEG | 80 END
2031-07-02: 70 END; 2031-08-05: NO CHANGES TO THE PLANS WILL BE ALLOWED AFTER THIS DATE WITHOUT THE CONCURRENCE OF THE STATE L&D, S&B AND S&C ENGINEERS; 2031-10-28: 71 END |  | 72 END
2031-07-02: 71X; 2031-10-28: 72X | 6
2031-07-02: 71C END; 2031-10-28: 21A,B END | 9
2031-10-15: NOT MEETING THIS DATE RESULTS IN THE PROJECT BEING DELAYED TO THE NEXT AVAIL. AD. SLOT !; 2031-10-28: 21 H,S END | X
69R END
*67C,D,U END
|  |  | NOT MEETING THIS DATE IMMEDIATELY PLACES THE AD DATE IN JEOPARDY ! | [5 empty] | 69 END
73 END
For Complete Descriptions of Activities Invlolved With Each Column, Refer to the Accompanying Document,"Column Descriptions" - Link provided above. |  |  | Column 4. Roadway Design Plans, Bridge, Structure, Utility, Sign, Signal, Lighting, Mitigation, Soundwall & Landscape plans and estimates and Project Specific Special Provisions complete. | [5 empty] | Column 10 *Prior to the Beginning of 67U, Activities 69 & 73 must end.
Note on A4: Prior to Column 1: Quality Control and Constructability Reviews and Scheduling of Pre- Advertisement Conference Based on District workload and local direction, on a project by project basis, the Project Manager communicates to the Team Members when the required final Quality Control Reviews and Constructability Reviews will be held. The completion of the plans, estimates, draft specifications, special provisions and copied notes and the subsequent quality control and constructability reviews of these items are the final steps in the plan development process. The review of the plans should include all plan subsets including highway, bridge, structure, utility, landscaping, noise wall, mitigation, signs, signal and lighting plans, including all special design drawings, details and summaries. All design work and functional certifications of completeness should be completed before these reviews begin. All plans must be tiffed to the Falcon Web Suite (Select Current Drawings) prior to these reviews. Any special contract language and all draft specifications, special provisions and copied notes and the draft proposed CPM schedule must be transmitted to the Scheduling and Contracts Division by the Project Manager prior to the date of the PAC Meeting.. Submission of the draft specifications, special provisions and copied notes must be coordinated with the State Specifications Engineer to ensure that final specifications are complete by the Column 2 date. The Project Manager must provide all team members the date by which all plan work must be completed so that these reviews can be held, and all applicable project tasks are in the schedule, such as – Hydraulic Review for Construction/PAC Project Task (51H), Final Landscaping Plans Project Task (53F), Develop Compensatory Mitigation Design Project Task (56), Final Traffic Control Device Plans Project Task (61C/D), Develop Retaining Structure Plans Project Task (62), Final Bridge Plans Project Task (64C/D), Plan Design @ PAC Project Task (65P). Adequate notice shall be given to provide a thorough review, comment submission and comment resolution prior to the scheduling of the Pre-Advertisement Conference. District specific guidelines can be developed for this process as long as the Pre-Advertisement Conference is completed by the Column 1. Column 1: All Plans Reviewed and Pre-Advertisement Conference Held. By this date, all QC and Constructability Reviews should be completed and the Pre-Advertisement Conference held. Also by this date, Programming Division should assign the Federal Number for federally funded projects. The following project tasks end on this date: Clear Railroad Agreements (68), Obtain Environmental Permits (70), Pre-Ad Conference Constructability/Bidability Review (71C), Pre-Advertisement Conference Date (71X). • Column 1 to 2 Duration: 10 Working Days
Note on B4: Column 2: PLAN COORDINATION REVIEW: Plan Revisions Complete and Plan Coordination Review Begins By this date, all revisions to the plans, including all subsets, must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed by this date so that the Plan Coordination Section can complete their review. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all final specifications, special provisions and copied notes and the final proposed CPM schedule must be transmitted to the Project Manager from the Scheduling and Contracts Division. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review). By this date, the Project Manager must notify the Plan Coordination Section of the electronic availability of the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager by this date, if not done previously For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 2 to 3 Duration: 8 Working Days
Note on C4: Column 3: Plan Coordination Review Complete and Project Manager Certification Begins By this date, the Plan Coordination Section completes their review and sends any comments to the Project Manager for incorporation into the plans. Upon completion, the plans are re-tiffed to the Falcon Web Suite-Plan File Room (Select Plan Coordination Review) and the Plan Coordination Section is notified. • Column 3 to 4 Duration: 5 Working Days
Note on D4: Column 4: Project Manager Certification Ends and Plan Coordination Processing Begins, Initiate EQD Certification and Verification By this date, the Project Manager must then certify to the District Location and Design Engineer that the project development process is complete and that the plans and estimate are ready for advertisement. Using Form LD-406, the District Location and Design Engineer then certifies (electronically) to the State Location and Design Engineer, the L & D Plan Coordination Section, the State Scheduling and Contract Engineer, the District Construction Engineer, and all of the team members that the complete plan assembly has received a QC and Constructability review and that the Pre Advertisement Conference has been held, adequate funding is in place for construction and the complete plan assembly is available electronically, providing the location and file name in the Falcon Web Suite. For Bridge only projects, the Project Manager will certify to the District Structure and Bridge Engineer, who will then certify the same information as above to the State Structure and Bridge Engineer and the other previously listed above. Also by this date, the Plan Coordination Section begins processing the Title Sheet for approval and submits to Programming Division to prepare the Funding Verification – PD-4. The following project tasks begin on this date: Approved Construction Plans (71), and Construction Authorization (79). Not Meeting This Date Immediately Places the Ad Date In Jeopardy! No changes to the plans will be allowed after this date without the concurrence of the State Location and Design, Structure and Bridge (if applicable) and Scheduling and Contract Engineers. Also by this date, the Project Manager submits PM-130 to the District Environmental Manager providing notification that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 4 to 5 Duration: 2 Working Days
Note on E4: Column 5: Plan Coordination Processing Ends and Contract Documents Development Begins, Initiate EQD Certification and Verification By this date, Plan Coordination notifies the Scheduling and Contract Division that the plans are ready for their review and use in the development of the contract documents, by transmitting the project documents assembly and Form LD-402. On this date, the Scheduling and Contract Division will establish a project file to contain permits and project specific special provisions. Location and Design will establish a link to this server from the plans location in Falcon. Scheduling and Contract Division begins building the control estimate and proposal. The Prepare for Advertisement Project Task (72) begins, on this date. Also by this date the following disciplines must provide the following information: Environmental Division shall transmit the NEPA environmental documents to the Scheduling and Contract Division. Department of Rail and Public Transportation shall transmit necessary railroad agreements to the Scheduling and Contract Division. • Column 5 to 6 Duration: 26 Working Days
Note on F4: Column 5: Attend PAC, Report, Discuss, and Review Findings Ends. Initiate EQD Certification and Verification By this date, the Project Manager conducts the Pre Advertisement Conference where reports and recommendations from all of the disciplines involved in the project are presented, discussed, and resolved. The Project Manager prepares a report of the PAC findings and actions immediately following the meeting. The report is distributed to all participants involved in that meeting, including the Scheduling and Contract Division. If additional project specific special provisions and copied notes are needed, the PM must immediately notify the Specifications section of the Scheduling and Contract Division to ensure they are prepared prior to the Biddability review. The District Environmental Manager (DEM) is notified that the plans and contract documents are ready for the Environmental Certification and PS&E Verification. The appropriate Project Manager/Coordinator will submit the LD-442 form to the DEM. PPMS activities 71X, 71C end, and 72 begins, on this date. · 5 to 6 Duration: 13 Working Days
Note on F5: Column 6: Contract Documents Development Complete and Title Sheet Signed and Environmental Certification and Verification Complete By this date, contract documents (electronic proposal) are completed for the Biddability Review and are available electronically at \\0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager and the District Construction Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Biddability team has all information needed for their review. Scheduling and Contract Division completes Initial Control Estimate and provides it to the PM and Programming Division for STIP/TIP Review. The Plan Coordination Section will notify the Project Manager when the title sheet has been approved and signed for Construction. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 6 to 7 Duration: 10 Working Days
Note on G5: Column 7: End Biddability Review by District Construction Engineer Staff By this date, the Biddability team furnishes a report of their findings to the Project Manager. The Project Manager posts these findings to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Scheduling and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. • Column 7 to 8 Duration: 8 Working Days
Note on H5: Column 8: Revisions to Contract Documents per Biddiblility Review Comments Ends By this Date, any necessary revisions to the contract documents, as the result of the Biddability review, are completed and ready for print. • Column 8 to 9 Duration: 3 Working Days
Note on I4: Column 9: ADVERTISEMENT SUBMISSION: Complete Plan Assembly to Plan Coordination with Adv. Requests By this date, all corrections and modifications to the advertisement package have been completed. All plans must be tiffed to the Falcon Web Suite-Plan File Room (Select Adv. Submission) and archived (Select Adv. Submission). The Project Manager, via Form PM-150, notifies the Plan Coordination Section that the final plans are available on the Falcon Web Suite. The advertisement print order will be provided to the Plan Coordination Section by the Scheduling and Contract Division. No Changes to the Plans or Contract Documents May Be Made After this Date. By Not Meeting This Date Results In The Project Being Delayed to the Next Available Advertisement Slot! For Sealing and Signing requirements, see the following Divisional Memoranda: IIM-LD-243, IIM-S&B-79, MD 317-09, TE-362 and IIM-CD-2013-12.01. • Column 9 to 10 Duration: 9 Working Days
Note on I21: PLEASE NOTE Between the time of submission to the Plan Coordination Section (Column 9) and the project showing (a minimum of 10 days after advertisement), no revisions will be made. The Reproduction Section will not permit any originals to be pulled from the plan assembly unless printing for advertisement has been completed and approval received from the Scheduling and Contract Division or Plan Coordination Section
Note on J4: Column 10: Advertisement Submission to Scheduling and Contracts Division Engineer and Print Reproduction for PS&E Begins By this date, the Plan Coordination Section will complete their review of the plans and notify the Scheduling and Contract Division, of the availability of the final plans. Printing is requested for only 2 sets for PS&E submission to the FHWA. The Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. The following project tasks end on this date: Monitor/Review Consultants – Location & Design (21A), Monitor/Review Consultants – Structure & Bridge (21B), Monitor/Review Consultants – Hydraulics (21H), Monitor/Review Consultants – Survey (21S), Obtain Coast Guard Permit (63), Approved Construction Plans (71), Plan Submission Date (72X). The following project tasks must be completed by this date, however, the actual end dates may vary for each particular project: Clear Utility Agreements (67C/D), Utility Relocations by Owners (67U), Acquire Right of Way (69/69R), Process Relocations (73). • Column 10 to 11 Duration: 5 Working Days Right of Way Certification The Right of Way/Utility Certification Date Project Task (69X) is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date.
Note on K4: Right of Way Certification This is the day the Right of Way and Utility Division will submit the right of way releases to the Scheduling and Contract Division. This must occur 4 weeks prior to Advertisement date. Key Event 69X
Note on L4: Column 11: Final PS&E to FHWA By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division to the FHWA. In the project schedule Prepare for Advertisement Project Task (72) ends and Advertise Project Task (80) begins. • Column 11 to 12 Duration: 22 Working Days
Note on M4: Column 12: Advertisement On this date, the project is advertised, and Advertise Project Task (80) ends. FHWA requires 15 working days to review and concur with the PS&E package for advertisement. Seven days is provided for response to FHWA comments and corrections to plans, if necessary. Printing of advertisement sets is completed following final approval by FHWA and is completed by the advertisement date.